Columbus State Community College Design Construction & Trades Department

Construction Management

CMGT 2241	Planning and Scheduling	Autumn 2022

## CMGT 2241-901-68903	Thursdays	5:30-10:20 PM	Davidson Hall 120

Instructor:	Dean Bortz	Office Hours: Mon-Wed 11 AM - Noon ( DELAWARE) Office:	 211 Davidson Hall		Tue-Thu 4-5PM (MAIN)

Phone:	614-287-5033 or 1-800-621-6407 X5033	or by appointment Fax:	614-287-3644

E-mail:	dbortz@cscc.edu

SYLLABUS

Course Description

A study of the management and coordination of construction projects utilizing systematic planning and scheduling. Various construction industry methods and techniques will be reviewed and practiced in simulated projects. The course stresses fundamental skills to develop, analyze and manage construction projects utilizing several scheduling methods, including: Work Breakdown Structures (WBS), Precedence Diagram Methods (PDM), and manual calculations of Critical Path Method (CPM) scheduling. Also, discussion of code and inspection-related items impacting the project schedule, supplemented with the use of Phoenix software.

Goals/objectives

By the end of this course, the student will be able to:

- Identify various types, purposes and uses of construction planning and scheduling techniques.

- Identify phases of a construction project for planning purposes.

- Identify construction project areas requiring inspection(s) and how delays (weather, material shortages, etc.) impact the construction project schedule.

- Demonstrate the ability to input scheduling information into computer software such as Phoenix scheduling software.

Textbook (Provided)

Construction Project Management Planning and Scheduling. Henry Naylor. OPTIONAL: BNi General Construction Cost Book, 2023 or similar.

References

CSCC ERC has a selection of materials relating to each topic given in the syllabus. Trade publications, professional organization literature and web sites are excellent resources: www.agc.org www.aspenational.com Computer Integrated Construction Project Scheduling. John Buttleswerth ISBN 978-0131114654

General Instructional Methods

The subject material will be presented in a seminar format with lecture, question and answers, and samples followed by a laboratory portion with exercises and presentations to illustrate the on-the-job applications of the subject presented.

Methods and Standards of Evaluation

Lab projects, in-class exercises, quizzes, journals and summative final project.

## Grade Composition

Participation -10% *CAEP – 10-% * Lab Projects - 30% * Quizz/Reflection - 25% * Final Project – 25% Grade ranges:	A = 90-100%	B = 80-89%	C = 70-79%	D = 60-69%	E = below 60%

## Special Course Requirements

Drawings and software shall be provided. Student shall provide architectural/engineering scales, note talking materials. Construction Master Pro Calculator 4065 recommended.

## Attendance

College policy will be followed and attendance will be noted each class period. Please advise your instructor prior to any situation that requires your absence.

## Cell phones and electronic devices

Cell phones must be turned off or put on vibrate during the class period. If you must use your cell phone during class, please inform the instructor of the emergency or personal business and leave the room or laboratory area. Anyone using a cell phone during class for any reason will be required to leave the room or laboratory area and will not be permitted to return until the telephone call is complete. Use of any other personal electronic device, except your calculator, is not permitted during class or during quizzes or exams. No assessments turned in after the due date will be accepted.

## College Policies

CSCC-required College Syllabus Statements on College Policies and Student Support Services may be found at www.cscc.edu/syllabus or on the CSCC homepage Quick Links “Syllabus Statements” tab.

Topics include, but are not limited to:

Institutional Learning Goals, Student Code of Conduct, Americans with Disabilities Act (ADA) Policy, Counseling Services, Title IX and Non-Discrimination, Tobacco Free College, Financial Aid Attendance Reporting, Audio/Video Recording of Class and Inclement Weather or Other Emergencies

## Your Instructor

Your instructor is also an advisor and mentor for the Construction Management (CMGT) program of study. You are encouraged to meet with your instructor to discuss your CMGT program goals, classes, career opportunities, transferring to a four year institution, scholarship and grant opportunities, and the field of Construction Management. If you are in a program of study other than CMGT, contact the Construction Sciences Department for assistance (614-287-5030)

## Student DesignOhio   www.designohio.org

DesignOhio is a national based, locally operated professional association that provides technical information, continuing education, professional networking, and product information to enhance communication among the building design and construction industry's disciplines and meet the industry's need for knowledge and navigation of construction documents. Members include architects, engineers, contractors, skilled trades, building owners, and material suppliers. DesignOhio’s improved communication and unprecedented teamwork help to develop innovative products and services of benefit to all involved in construction. The student member has the opportunity to attend the monthly education and training events and students are encouraged to investigate how this affiliation will enhance career and networking opportunities. Prof. Dean M. Bortz, FCSI, CCPR, CDT is the current student advisor. (614-287-5033, dbortz@cscc.edu)

## American Society for Safety Professionals (ASSP) Student Chapter

The oldest safety association in the world now has a student chapter at CSCC. This is an international professional association that provides networking, credentialing, and education to current and aspiring safety professionals. Prof. Jeffrey Bates, Ph.D., is the current faculty advisor (614-287-3652, Jbates@cscc.edu)

Course Schedule (Subject to Change)

| Week | Unit of Instruction | Learning Objectives | Assignments And Assessments | Journal Due Dates |
| --- | --- | --- | --- | --- |
| 1 31 AUG | Course introduction LABOR DAY MON 4 SEP | Demonstrate understanding of course objectives and expectations | Read CH 1 Pp 1 – 9 | Q 1 & 2 Page 9 Due not later than (NLT) start of next class |
| 2 7 SEP | Planning & Scheduling – WBS, Bar Chart theory and practice | Demonstrate comprehension of WBS | Read CH 2 Pp 11-28 PROJECT 1 | Q 3 Pg 281 Due NLT start of next class |
| 3 14 SEP | History of Planning & Scheduling; Gantt network theory and principles; logic and AON diagramming format | Demonstrate comprehension of Gantt (Bar) chart design | Read CH 3, 4, 13 PROJECT 2 | Q #1 Page 45 Q #1, Page 64 Q #4, Page 238 |
| 4 21 SEP | Converting project information into time and effort by extrapolating calculations from references (Walker’s, RS Means, BNi) | Demonstrate comprehension of required calculations to determine time and effort | Read CH 3 ,4, 13 PROJECT 3 | Q #3 Page 45 Q # 2 Pp 64-65 Q #1 Page 238 |
| 5 28 SEP | PDM network, principles and theory; logic and PDM forms No Day Classes 3 Oct | Demonstrate comprehension of project logic | Read CH 4, 5 QUIZ PROJECT 4 | Q # 5 Page 65 Q #1 Page 79 |
| 6 5 OCT | Schedule computations; calendar data; early start and finish network calculations OPFMA 12 OCT Makoy Ctr | Demonstrate comprehension of calculating project early finish | Read CH 5, 6 QUIZ PROJECT 5 | Q #5 Page 80 Q # 1 Page 101 |
| 7 12 OCT | Late start & finish; float network calculations; establishing constraint data OTEC 17 & 18 OCT Cbus Convention Ctr | Demonstrate comprehension of calculating project duration & CP | Read CH 8, 9 Project 6 | Q #1 Page 136 Q #1 Page 160 |
| 8 19 OCT | Translating PDM information and determining schedule logic | Demonstrate comprehension of PDM interpretation | Read CH10,11 Project 7 | Q #1 Page 184 Q #1 Page 195 |

Course Schedule (Subject to Change)

| Week | Topic | Projects Assessments | Text Chapters and In Class | Text Test Your Knowledge and Activities |
| --- | --- | --- | --- | --- |
| 9 26 Oct | Converting information from analog to digital CDT BOOT CAMP 29 OCT | Demonstrate comprehension of converting analog to digital data | Read CH 12 Project 8 | Q #1 Page 195 Appendix “D” Appendix “E” |
| 10 2 Nov | CPM Data Reports and Analysis | Demonstrate comprehension of standard reports | Read CH 13 | Q #1 Page 238 Appendix “C” |
| 11 9 Nov | Specific standard and custom formatting computer reports VETERANS’ DAY FRI 10 NOV | Demonstrate comprehension of developing reports | Warehouse Project | Initial Schedule Due |
| 12 16 Nov | Reducing project duration; Final Project Introduction | Demonstrate comprehension of how to reduce project duration. | Warehouse Project |  |
| 13 23 Nov | THANKSGIVING 22 NOV – 26 NOV |  |  |  |
| 14 30 Nov | Lab work session; related code issues, inspections and weather delays | Demonstrate comprehension of including inspections and weather days into a schedule | Warehouse Project RETURN TEXT BOOK |  |
| 15 7 Dec | FINAL PROJECT TEAM PREENTATIONS | Demonstrate comprehension of putting an entire project together | Lab Time | Final Project Due 8 Dec |
| 16 14 Dec |  |  |  | GRADUATION 15 DEC 11 AM |

This Page Intentionally left blank

------------------- (Fill out the following information - detach page - return to instructor)---------------------

# Columbus State Community College Construction Management Program Laboratory Experience

Informed Consent & Waiver

In consideration of being granted the opportunity to participate in this on campus / off-campus activity, I do hereby release and forever discharge all Columbus State faculty, associates, administrators, fellow classmates and alumni (and their agents) who arranged, advised, supervised, scheduled, and other pertinent functions related to this activity for myself or my heirs, executors, administrators, (and assigns) and hereby release and hold harmless the above aforementioned from all claims, legal actions, and causes of action for personal injury or any other damage now existing or which may arise out of (up to and including death) in any way related to their negligence or other conduct associated with this activity in this course.

I have read and I do fully understand all of the above provisions. I certify here that I am a student at Columbus State Community College and I am at least 18 years of age. I will abide by all policies and procedures outlining student behavior and misconduct during this laboratory/function. If I choose to not follow the policies and procedures of student behavior outlined in the Columbus State student handbook, I acknowledge that student misconduct charges can, and will, be brought against me.

I consent to my picture being taken during class and/or used for promotional purposes for the program. I have read and understand the College Policy Requirements as stated in the Syllabus. I understand that late submission of work without prior permission (or without the proper documentation) will result in a grade of zero on the related assignments and that lack of participation will result in lowering my final grade. Reports and/or presentations submitted as assignments become the property of the Construction Management program and may be retained for other educational purposes.

Semester-Year: Autumn 2023

Student Name (Print):

Student Signature:

Date: 	 Cougar ID Number:

Course # CMGT-2241-001-80081	Instructor’s Name: Dean M. Bortz, FCSI, CDT, CCPR

This Page Intentionally left blank